## Legend
Low | not a priority, may not be implemented
Medium | priority, but nice to have, dependent on available budget
High | necessary, will prevent requirement from passing or is associated with functionality guaranteed by requirements document
Complete | feature implemented or bug resolved

## Bugs
Discovery | [9 empty] | Resolution/Completion
Index | Date | Person | Version | Priority | Title | Description | Recreation | Comments | Commit | Date | Developer | Description | Version | Commit | Comments
1 | 2017-12-28 | Antonio Alexander | 0.9.21 | Low | Startup Tree option when no items | In the edit automatic deployment interface, the startup tree option will not remove the '<no startup items>' entry when items are added. | Should be able to recreate by adding a new target, then trying to add a startup item, then cancelling the operation. |  | 2fd83820e0fe97684a970298fbcb7807ada0d873 | 2017-12-28 | Antonio Alexander | Found that issue was related to how items were removed and added from tree, normalized that and issue was fixed. | <v0.9.29 | 88addfb8d2519c94815e7b9befe6db9fef9f4314
2 | 2017-12-30 | Antonio Alexander | 0.9.21 | Medium | Network Interface doesn't make sense? |  |  |  | 2fd83820e0fe97684a970298fbcb7807ada0d873 | 2018-01-12 | Antonio Alexander | Re-worked the interface altogether using a separate interface for input and a main interface with two trees. | >0.9.33 | 7b22881045195c2699ae2799bd91c130c53f15ce
3 | 2017-12-30 | Antonio Alexander | 0.9.x | High | Bad Persistance of USB filtering | Doesn't seem to stick when set in the configuration interface | If you go to configuration (or the target selection window) and enable usb filtering, then close and re-open, the configuration interface and the target selection interface don't both show that its enabled/set. |  |  | 2018-01-03 | Antonio Alexander | Found that the select that would set/unset the pict icon for usb filtering was reversed in the target selection interface, so persistent, but displayed incorrectly | v0.9.33 | 5357c294c2c04cf46912d5bf1b7686e05091f78b
4 | 2017-01-02 | Antonio Alexander | 0.9.29 | Medium | Activation doesn't close Software Activation Window | When activating a trial license (or any license?), although successfully activated, the software activation window isn't automatically closed. |  | tew_1, TD-002 | 4b3e99b8f6c3537ec2d61e34b1f10fadcb407ac2 | 2018-01-03 | Antonio Alexander | Resolved by removing execution of the 'helper.exe' so that activation has to occur from the application and not outside of it. | v0.9.33 | 5357c294c2c04cf46912d5bf1b7686e05091f78b
5 | 2017-01-02 | Antonio Alexander | 0.9.29 | - | Trial Mode, USB filtering not forced | USB filtering should be forced and disabled for trial mode. | After succesful trial license activation, the target selection window does not have usb filtering enabled and disabled/greyed. | tew_1, TD-002 | 4b3e99b8f6c3537ec2d61e34b1f10fadcb407ac2
6 | 2017-01-02 | Antonio Alexander | 0.9.29 | High | Trial Mode, invalid time limit | Trial time limit was 30 days and not 7 days | Upon successful trial license activation the application sdays there are 30 days left when there should only be 7. | tew_1, TD-002 | 4b3e99b8f6c3537ec2d61e34b1f10fadcb407ac2
7 | 2017-01-02 | Antonio Alexander | 0.9.29 | High | Failed Activation | Only activcating for trial mode works. Client, Client Plus and Developer full activation don't work. | Attempt to activate (with a valid license) anything other than trial or client mode and you'll find that it fails consistently with error 70. | tew_1, TD-002 | 4b3e99b8f6c3537ec2d61e34b1f10fadcb407ac2 | 2018-01-03 | Antonio Alexander | Fixed by changing the trigger code in the configuration | v0.9.33 | 5357c294c2c04cf46912d5bf1b7686e05091f78b
8 | 2018-01-02 | Antonio Alexander | 0.9.29 | Medium | Issue with target selection on Multiple Interfaces | When looking at the target selection window and the same target is on two interfaces (i.e. the usb and ethernet) both of them don't show up when they should | Connect a target to the application machine with USB and Ethernet and refresh target selection | tew_1, TD-003 | 4b3e99b8f6c3537ec2d61e34b1f10fadcb407ac2
9 | 2018-01-02 | Antonio Alexander | 0.9.29 | Low | Add FPGA button doesn't reset |  | When you click the add fpga button in the fpga bitfile selection interface, it doesn't automatically reset. | tew_1,TD-004 | 4b3e99b8f6c3537ec2d61e34b1f10fadcb407ac2 | 2018-01-02 | Antonio Alexander | Fixed by ensuring inside the while loop and setting to latch on release | >v0.9.29 | e2c4794bf94905dd550d509fe30c523f7e9be25f
10 | 2018-01-02 | Antonio Alexander | 0.9.29 | High | Unable to copy FPGA bitfiles | When adding a bitfile to copy over, it always fails | Go to the FPGA bitfile selection interface via the automatic configuration window or the maunal fpga installation window and attempt to add an FPGA outside of the configured bitfile directory. | tew_1,TD-004; still get an error on cancel (erro 43), can manually copy to bitfile directory and refresh successfully | 4b3e99b8f6c3537ec2d61e34b1f10fadcb407ac2 | 2018-01-02 | Antonio Alexander | Fixed by ensuring that configuration was working (should be created silently) and that it was using the configured directory | >v0.9.29 | e2c4794bf94905dd550d509fe30c523f7e9be25f
11 | 2018-01-02 | Antonio Alexander | 0.9.29 | Low | Update Firmware Feedback Generic | Positive feedback after updating the firmware is generic and not specific | Manually update the target firmware and observe positive/negative feedback | tew_1, TD-005 | 4b3e99b8f6c3537ec2d61e34b1f10fadcb407ac2 | 2018-01-02 | Antonio Alexander | Updated the VI that had the string constants, found that the case structure had some undefined cases. | >v0.9.29 | e2c4794bf94905dd550d509fe30c523f7e9be25f
12 | 2018-01-02 | Antonio Alexander | 0.9.29 | Low | Product Filter functionality intermittent | Seems that when selecting targets in automatic deployment configuration window, the target/product filtering doesn't work consistently |  | tew_1, TD-007 | 4b3e99b8f6c3537ec2d61e34b1f10fadcb407ac2
13 | 2018-01-02 | Antonio Alexander | 0.9.29 | Low | Network doesn't remain open if opened | ?? |  | tew_1, TD-007 | 4b3e99b8f6c3537ec2d61e34b1f10fadcb407ac2
14 | 2018-01-02 | Antonio Alexander | 0.9.29 | Low | Automatic Deployment Save doesn't default to right folder | When you click save in automatic deployment configuration it doesn't default to the right folder |  | tew_1, TD-007 | 4b3e99b8f6c3537ec2d61e34b1f10fadcb407ac2
15 | 2018-01-02 | Antonio Alexander | 0.9.29 | High | Automatic Save has negative feedback on cancel | When you click save in automatic deployment configuration and cancel, you receive negative feedback saying that you cancelled. |  | tew_1, TD-007 | 4b3e99b8f6c3537ec2d61e34b1f10fadcb407ac2 | 2018-01-02 | Antonio Alexander | Fixed by ensuring that the negative feedback only occurred if no error came from the selection dialog | >v0.9.29 | e2c4794bf94905dd550d509fe30c523f7e9be25f
16 | 2018-01-02 | Antonio Alexander | 0.9.29 | High | IP Address validation fails on empty | When IP address left empty for network configuration, the validation fails. |  | tew_1, TD-009
17 | 2018-01-02 | Antonio Alexander | 0.9.29 | High | Workflow odd on multiple targets with cancel/failure | ?? |  | tew_1, TD-010
18 | 2018-01-02 | Antonio Alexander | 0.9.29 | Low | Error on startup application deployment | Unable to deploy startup application du to dependency?, feedback is generic |  | tew_1, TD-010
19 | 2018-01-02 | Antonio Alexander | 0.9.29 | High | Multiple Target Deploy Failures | When deploying to multiple targets, some actions seem to fail unnecessarily. |  |  |  | 2018-01-02 | Antonio Alexander | Fixed by ensuring there wasn't a mismatch for product types, I believe the string stored was not matching the search aray | <v0.9.33 | f2db6b3b47642c32524fca575e96e55e4b9b7373
20 | 2018-01-16 | Antonio Alexander | 0.9.34 | High | Copying FPGA bitfiles Broken | Found that when creating an auto-deployment configuration, the bitfile wasn't getting copied into the auto-deployment | Create a simple configuration with one target and a single fpga deployment, if you extract the archive, you'll see that it doesn't have the bitfile in it. |  | 31094cdc2b0eb03e2907ba34687236c45e733a4a | 2018-01-16 | Antonio Alexander | Resolved by ensuring that the paths were interpretted as being absolute until it was copied into the configuration archive | v.0.9.35 | 26f87b94d76bbb768196c85497a1265febe0341e
21 | 2018-01-17 | Antonio Alexander | 0.9.36 | High | FPGA bitfile path invalid when editing config | When you attempt to edit an automatic deployment configuration, it loads the bitfile path with its relative path and as a result can't be copied into the archive when you attempt to save. |  |  | 171aa4f8ad6db3292020fd5cbb49ed7f85a01d38 | 2018-01-17 | Antonio Alexander | Resolved by looking for FPGA bitfiles and extracting them into a temporary directory for the editing process | v0.9.36 | e271235cba4c02136f77973880e4fb175e986d38
P

## Features
Request | [6 empty] | Implementation/Completion
Index | Date | Person | Title | Description | Priority | Comments | Date | Developer | Description | Version | Commit | Comments
1 | 2017-12-01 | David Taylor | Add Startup without target attached | Often after performing an initial installation, the startup.rtexe may be re-built or a new version of the FPGA implemented. A developer should be able to update the startup application without the target attached and send to the client for installation. | Medium | Implemented, but initial configuration requires that the target be attached. With feature#2, its possible for a client to populate the target data and send to a developer via the SQLite file. | 2017-12-19 | Antonio Alexander | Implemented by parsing the appbuilder.cdf file to get the product id and information post installation | <v0.9.20 | 6a66b5e665a850abe871cf1c878c41c25f207a6e
2 | 2017-12-01 | Antonio Alexander | Be able to configure automatic deployments without targets attached | Need to have some way to browse and re-create a configuration if the target is not connected. Feasible to have the target connected the first time (maybe), but subsequent times are not feasible, esp for a developer. | Medium |  | 2017-12-19 | Antonio Alexander | Implemented by using SQLite to quietly (and deliberately from configuration) store the available software for a given target offline. | <v0.9.20 | 6a66b5e665a850abe871cf1c878c41c25f207a6e
3 | 2017-12-28 | Antonio Alexander | Explicit Software Modes | Allow the application to be able to differentiate between developer and client/end-user versions and enable/disable system components as needed. The general goal would be to allow/restrict access to: (1) manual mode, (2) create/edit automatic configuration and (3) install/deploy automatic configuration. | Low | Could probably be done using three bits in the software activation if in full mode, can add to the fg_security data type along with the full/trial enum. | 2018-01-02 | Antonio Alexander | Implemented by storing data in license to differentiate what is accessible | <v0.9.29 | 182732764f3fd1d5cfa52baf095e3fc88fd1fe57 | If enabled, trial mode can set the version on the fly.
4 | 2017-12-28 | Antonio Alexander | Automatic Deployment MD5 | Although already in a zip, an MD5 file that can be supplied or pasted can help verify that the file is in good shape after being downloaded. | Low | Can implement using the MD5 ability inside LabVIEW and creating a file dialog to select the MD5 file or paste in the MD5 text.
5 | 2017-12-28 | Antonio Alexander | Post Install Step | Allow developers to code a plugin based lvlibp file that can be used to run a VI upon completion of installation. This could be used to do things such as setup opkg or run commands via putty to configure the system. | Low | Could be best implemented using an external interface (lvlibp) and using a plugin architecture to extract the appropriate lvlibp from the automatic configuration (7z) file, load and execute (providing feedback).
6 | 2017-12-28 | Antonio Alexander | Recipe Failure Workflow | Allow configuration to 'ignore' failure of steps? | Low | The issue is that often when certain steps fail, the recipe process halts and if no-one is watching, it'll wait indefinitely. This isnt always ideal.
7 | 2017-12-28 | Antonio Alexander | Startup.rtexe's can dictate dependencies | Code software such that its possible to just add an rtexe and it'll install the appropriate software automatically as configured? | Medium | Probably not difficult, but will create some specific ambiguity when it comes to automatic deployment.
8 | 2017-12-28 | Antonio Alexander | Optimize recipe creation to minimize reboots. | There are a couple of situations where the recipe could remove a couple of the reboots to speed up deployment time (rebooting takes a lot of effort/time). | Low |  | 2018-01-17 | Antonio Alexander | Updated the create recipe to omit steps if there wasn't any configuration for them, also added an additional step that would select the appropriate recipe by using the target, removed all other queries for product selection in the recipe selection. Should be more efficient. | v0.9.36 | 171aa4f8ad6db3292020fd5cbb49ed7f85a01d38
9 | 2017-12-28 | Antonio Alexander | Import/export offline software databases | Would be nice to be able to import or export offline hardware information (i.e. developer is remote and doesn't have hardware available to put togther an automatic deployment configuration). | Low
10 | 2017-12-28 | Antonio Alexander | Add checks for modified items (changes sensed, do you want to disc ard?) | For interfaces, when you change a value, it remembers that you changed it (not what it was) and there's a prompt to discard changes when you attempt to close the interface | Medium |  | 2018-01-03 | Antonio Alexander | Implemented, not sure when. | <0.9.33 | 5357c294c2c04cf46912d5bf1b7686e05091f78b
11 | 2017-12-28 | Antonio Alexander | validation for ip address entry | When entering ip address (notable ip address/gateway) there should be input validation to ensure its correct | High | Only really used for static ip mode. | 2017-12-31 | Antonio Alexander | Implemented to validate if not zero, only used for ip and subnet mask | <0.9.29 | c9bcfd575afa60c5c8639d650c01f7531d756d6f | No checks done to ensure subnet mask is valid.
12 | 2017-12-28 | Antonio Alexander | three button interface on authentication failure | Should have the ability to bypass, re-enter or cancel | Medium | It's too easy to mis-type authentication information, there should be a workflow to account for it | 2017-12-29 | Antonio Alexander | Modifed so that it provides options as described | <0.9.29 | 8a58b10abee36dcafe4c07367c627346e5e3bbcd | Workflow stll doesn't allow for multiple usernames/passwords.
13 | 2017-12-28 | Antonio Alexander | Add option to reboot automatically for manual actions? | For software operations the target often has to be in installation mode, there may be value to be able to perform all the functions atomically rather than automatically rebooting for each step (puts more onus on the user to have the target in the right state). | Low | May be more complicated than necessary
14 | 2017-12-28 | Antonio Alexander | Cant uninstall components | There currently isn't a way to uninstall componenents | Low
15 | 2017-12-28 | Antonio Alexander | Cant enable/disable individual items in software sets | Currently software sets are all/none and you can't invididually include items | Low
16 | 2018-01-02 | Antonio Alexander | Software Activation Feedback | Upon successful activation, the software activation window doesn't automatically close or indicate a change in type (i.e. switching from trial to full mode). | Low |  | 2018-01-03 | Antonio Alexander | Resolved by updating the titlebar | v0.9.33 | 5357c294c2c04cf46912d5bf1b7686e05091f78b | Somewhat unnecessary since it closes after successful activation
17 | 2018-01-02 | Antonio Alexander | Confirmation inputs on Manual Operations | Would be nice to have confirmation inputs as a 'final action' for all manual actions, could be enabled/disabled via configuration (never confirm again button). | Low | tew_1, td-006
18 | 2018-01-02 | Antonio Alexander | Multiple Target Offline Synchronization | Would be useful to be able to synchronize offline with multiple targets | Low | tew_1, TD-009
19 | 2018-01-02 | Antonio Alexander | Automatic Deployment Save Compression Minimized | Window that compresses configruation should be minimized | Low | tew_1, TD-009
20 | 2018-01-02 | Antonio Alexander | Multiple Target Action Feedback | Would be nice to see what target is currently being deployed to (not even IP address just x/y) | Low | tew_1, TD-010 | 2018-01-04 | Antonio Alexander | Updated the recipe control feedback to look at status to determine which target it was currently on. Only displays x/y | >v0.9.33 | 2f3a43148f11d9c418eb14e24e3c9f178513ddd9
21 | 2018-01-02 | Antonio Alexander | Startup Application with Dependencies | Ability for system to deploy a startup.exe (cdf) with dependencies is gray right now, seems to fail more often than not, but should be an express feature | Low | tew_1, TD-010
22 | 2018-01-10 | Antonio Alexander | Manual software set install with add-ons | When done manually, could add interface to check the software set and provide selection to choose add-ons from those available via software set, could also add filter for software set componets on automatic deployment configuration | Low